## Sayfa1
MOBILE PART
Use Cases
[10 empty] | Tester |  | 60 % OF THE PROJECT
Login | 2020-03-17 | 2020-03-21 | 2020-04-04 | 2020-04-16 |  | 2020-05-02 | 2020-05-09 | 2020-05-19 |  |  |  |  | Not Working | Not Finished | Finished Working
Correct Credentials Check | [9 empty] | Oğulcan Delice, Mert Şağban
Having '@' Check | [9 empty] | Oğulcan Delice, Mert Şağban
Warning Message Check | [9 empty] | Mert Şağban, Oğulcan Delice
Wrong Credentials Check | [9 empty] | Oğulcan Delice, Mert Şağban
Emptiness Check | [9 empty] | Oğulcan Delice, Mert Şağban
SignUp | 2020-03-17 | 2020-03-21 | 2020-04-04 | 2020-04-16 |  | 2020-05-06 | 2020-05-09 | 2020-05-19
Correct Credentials Check | [9 empty] | Oğulcan Delice, Mert Şağban
Having '@' Check | [9 empty] | Oğulcan Delice, Mert Şağban
Warning Message Check | [9 empty] | Mert Şağban, Oğulcan Delice
Wrong Credentials Check | [9 empty] | Oğulcan Delice, Mert Şağban
Emptiness Check | [9 empty] | Oğulcan Delice, Mert Şağban
Search Need | 2020-03-20 | 2020-03-27 | 2020-04-07 | 2020-04-16 |  | 2020-05-03 | 2020-05-10 | 2020-05-19
Related Search Result | [9 empty] | Mert Şağban
Search By Need | [9 empty] | Mert Şağban, Oğulcan Delice
Search By Name | [9 empty] | Mert Şağban, Oğulcan Delice
Searching Case Sensitive | [9 empty] | Mert Şağban, Oğulcan Delice
Warning Messages If No Need Found In The Searched Criteria | [9 empty] | Mert Şağban
Create Chat Screen | 2020-04-05 | 2020-04-08 | 2020-04-10 | 2020-04-16 |  | 2020-05-04 | 2020-05-10 | 2020-05-18
Creating Chat Screen Between Users | [9 empty] | Mert Şağban
Sending Chat Among Users Simultaneously | [9 empty] | Mert Şağban, Oğulcan Delice
Creating Corresponding Chat Screen Between Users | [9 empty] | Mert Şağban, Oğulcan Delice
Sending Chat Anyways | [9 empty] | Mert Şağban, Oğulcan Delice
Holding Exisisting Chats In Distinct Section | [9 empty] | Oğulcan Delice, Mert Şağban
Select Need | 2020-03-19 | 2020-03-26 | 2020-04-07 | 2020-04-16 |  | 2020-05-01 | 2020-05-06 | 2020-05-19
Warning Message If No Need Found In The Selected Area | [9 empty] | Mert Şağban, Oğulcan Delice
Select Need From The Map | [9 empty] | Mert Şağban, Oğulcan Delice
Offer Help <<extent>> | 2020-03-21 | 2020-03-25 | 2020-04-03 | 2020-04-16 |  | 2020-05-04 | 2020-05-12 | 2020-05-19
Offer Help Button For Selected Need | [9 empty] | Oğulcan Delice
Offer Help Button For Chat Creation | [9 empty] | Oğulcan Delice, Mert Şağban
View Offers | 2020-03-21 | 2020-03-25 | 2020-04-03 | 2020-04-16 |  | 2020-05-07 | 2020-05-11 | 2020-05-19
View all posted Needs by the user | [9 empty] | Oğulcan Delice, Mert Şağban
Accept Need | [5 empty] | 2020-05-04 | 2020-05-11 | 2020-05-19 |  |  |  | 40 % OF THE PROJECT
Accept Button For Corresponding Need | [9 empty] | Oğulcan Delice, Mert Şağban
Warning Message Before Accept | [9 empty] | Oğulcan Delice, Mert Şağban
Reject Offer | [5 empty] | 2020-05-04 | 2020-05-11 | 2020-05-19
Reject Button For Corresponding Need | [9 empty] | Oğulcan Delice, Mert Şağban
Warning Message Before Reject | [9 empty] | Oğulcan Delice, Mert Şağban
Requet Need | [5 empty] | 2020-05-03 | 2020-05-10 | 2020-05-19
Request Button For New Need On Map | [9 empty] | Oğulcan Delice, Mert Şağban
Description Text Inside Request Screen | [9 empty] | Oğulcan Delice, Mert Şağban
Selecting Criteria Inside Request Screen | [9 empty] | Oğulcan Delice, Mert Şağban
Using Current Location Info Inside Request Screen | [9 empty] | Mert Şağban
Share Location | [5 empty] | 2020-05-02 | 2020-05-11 | 2020-05-19
Using Location On Map | [9 empty] | Oğulcan Delice, Mert Şağban
Google Maps API Implementation | [5 empty] | 2020-05-01 | 2020-05-13 | 2020-05-19
Implemented Maps | [9 empty] | Oğulcan Delice, Mert Şağban
Use Gps | [5 empty] | 2020-05-02 | 2020-05-11 | 2020-05-19
Using Gps to extract exact location data | [9 empty] | Oğulcan Delice, Mert Şağban
WEB PART
Use Cases
[9 empty] | Tester | Tester | 60 % OF THE PROJECT
Login | 2019-12-24 | 2020-03-21 | 2020-04-16 |  | 2020-05-05 | 2020-05-09 | 2020-05-19
[13 empty] | Not Working | Not Finished | Finished Working
Correct Credentials Check | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Having '@' Check | [8 empty] | Mert Yılmaz
Warning Message Check | [8 empty] | Mert Yılmaz
Wrong Credentials Check | [8 empty] | Mert Yılmaz
Emptiness Check | [8 empty] | Enes Malik Kuluk
SignUp | 2019-12-24 | 2020-03-21 | 2020-04-16 |  | 2020-05-06 | 2020-05-09 | 2020-05-19
Correct Credentials Check | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Having '@' Check | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Warning Message Check | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Wrong Credentials Check | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Emptiness Check | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Banned Check | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
SignOut | 2019-12-24 | 2020-03-21 | 2020-04-16 |  | 2020-05-05 | 2020-05-11 | 2020-05-19
Signs out and returns to Home Screen | [8 empty] | Enes Malik Kuluk
Search Need | 2019-12-24 | 2020-03-27 | 2020-04-16 |  | 2020-05-06 | 2020-05-12 | 2020-05-19
Related Search Result | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Search By Description | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Search By Type | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Search By City | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Searching Case Sensitive | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Warning Messages If No Need Found In The Searched Criteria | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Add Need (Request Need) | 2019-12-24 | 2020-03-27 | 2020-04-16 |  | 2020-05-07 | 2020-05-11 | 2020-05-19
Enter Description | [8 empty] | Enes Malik Kuluk
Enter City | [8 empty] | Enes Malik Kuluk
Warning Messages for any blank fields | [8 empty] | Enes Malik Kuluk
Google Maps API Implementation | 2019-12-24 | 2020-03-25 | 2020-04-16 |  | 2020-05-01 | 2020-05-13 | 2020-05-19
Implemented Maps | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
View User Needs | 2019-12-24 | 2020-03-27 | 2020-04-16 |  | 2020-05-07 | 2020-05-11 | 2020-05-19
View all posted Needs by the user | [8 empty] | Mert Yılmaz
View Offers | 2019-12-24 | 2020-03-27 | 2020-04-16 |  | 2020-05-07 | 2020-05-11 | 2020-05-19 |  |  |  | 40% OF THE PROJECT
View all posted Needs by the user | [8 empty] | Mert Yılmaz
Offer Help <<extent>> | 2019-12-24 | 2020-03-25 | 2020-04-16 |  | 2020-05-08 | 2020-05-11 | 2020-05-19
Offer Help Button For Selected Need | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Accept Need |  |  |  |  | 2020-05-04 | 2020-05-11 | 2020-05-19
Accept Button For Corresponding Need | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Reject Offer |  |  |  |  | 2020-05-04 | 2020-05-11 | 2020-05-19
Reject Button For Corresponding Need | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Approve Need |  |  |  |  | 2020-05-04 | 2020-05-11 | 2020-05-19
Approve Button For Corresponding Need | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Create Chat Screen |  |  |  |  | 2020-05-01 | 2020-05-13 | 2020-05-19
Creating Chat Screen Between Users | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Creating Chat Screen For Corresponding Need | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Better UI/Frontend |  |  |  |  | 2020-05-01 | 2020-05-15 | 2020-05-19
UI Improvements | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Chat Screen Improvements | [8 empty] | Mert Yılmaz | Enes Malik Kuluk
Admin Panel |  |  |  |  | 2020-05-08 | 2020-05-13 | 2020-05-19
Ban User Feature | [8 empty] | Enes Malik Kuluk
View Activities Of Reported Users | [8 empty] | Mert Yılmaz
UnBan User Feature | [8 empty] | Enes Malik Kuluk
Decline button to delete report of an user | [8 empty] | Mert Yılmaz
Report User |  |  |  |  | 2020-05-05 | 2020-05-10 | 2020-05-19
Reporting user according to chat log | [8 empty] | Mert Yılmaz